## QC Patch
Patch Date |  |  |  |  | Release For | Revision Diff | Merge Request | Components
5/25/2026 |  |  |  |  | TAG-prod_QC_250526-2 | Client: [ 11808c3d - 06552203 ] |  | Component : - [ CTCL Client, GATS ]
FTP Path |  |  |  |  | Download Link |  |  |  |  | SHA256 Checksum
ftp://192.168.209.145/shipnotes/releaseQC/Fusion_client64bit/client_side/TAG-prod_QC_250526-2.zip |  |  |  |  | ftp://dtftp@192.168.209.145/shipnotes/releaseQC/Fusion_client64bit/client_side/TAG-prod_QC_250526-2.zip |  |  |  |  | 0f313cf861b75116f9bff49e4eb51f1f2b02e7cdd5e55c4c81dc089c02196530
Jira ID | Summary | Issue Type | Priority | Severity | Status | Assignee | Dev Team | QA Assignee | QA Team
GETSCTCL-13506 | For NSE/BSE EQ/FO Exchange wrong "llogtime" displayed for "Trade Modification Request (5610)" igreekcode in Database Trade history table. | Bug | High |  | Testing In Progress | Ankita Jaiswal | Team Mahendra | Anant Giri | Team Ajay
GETSCTCL-12167 | Derived SYN Stock option requirement in Basket Algo | New Feature | Medium |  | In Progress | Rahul Shivaji Magar | Team Rahul | Shubham Bendre | Team Ajay
GETSCTCL-14169 | Delay in NSE-SLBM Broadcast Updates in CTCL Terminal Market Watch via GMBS | Live Issue | Highest |  | Done | Vaibhav Tale | Team Nikunj | Vaibhav Rajaram Kumbhar | Team Ajay
GETSCTCL-14261 | In Alt+E Arbitrage, rules contaning Vega, Product Diff and Ref Price(Absolute, product, spread) as Diff Type getting uploaded as "Abs." with Advance Save File functionality. | Bug | High |  | Done | Priyanka Salunkhe | Team Jigar | Faizan Raiba | Team Hemant
GETSCTCL-14161 | Cash To Cash Rules | Sub-task | Medium |  | Done | Ram Sarang | Team Nikunj
GETSCTCL-14413 | Optimize Build Hang Process in VS | Task | Medium |  | Done | Nikunj.Rathod | Team Nikunj
GETSCTCL-14428 | In Optimus Client getting crash on Ctrl+R basket when we change execution action to mute in basket detail watch and modify | Bug | Highest |  | Done |  | Team Rahul | Shubham Bendre | Team Ajay
GETSCTCL-14456 | In the Optimus Greek plugin, the focus does not move from left to right on the Greek Simulation Report window. | Bug | Low |  | Done | Rohan Phadatare | Team Nikunj | Gurudas Abaso Jadhav | Team Ajay
GETSCTCL-12108 | NSE FO Version 9.48 - Updates for existing transcodes for 1833 , 7201 . additional transcodes for 17208, 17211. Additional message rate control at Milisecond level | Task | Medium |  | Done | Soham Patil | Team Mahendra
GETSCTCL-1 | Reverse Trade Cancellation Mechanism | Epic | Medium |  | Done | Prasad MG
GETSCTCL-13583 | Issue with Position Not Showing in Greek (F7) Window after save Portfolio it get displayed. | Live Issue | High |  | Done | Sujit Tembhurne | Team Nikunj | Hanumant Sawant | Team Ajay
GETSCTCL-13145 | Implement Synthetic Future Spot Derivation Logic | Sub-task | Medium |  | Done | Rahul Shivaji Magar | Team Rahul
GETSCTCL-13953 | SBOM - Greeksoft Technologies Private Ltd | Task | Medium |  | Done | Vineet Kumar | Team Nikunj
GETSCTCL-13996 | In Alt+S Arbitrage, when uploading saved Advance Load file, rules not getting uploaded. | Bug | High |  | Done | Priyanka Salunkhe | Team Jigar | Faizan Raiba | Team Hemant
GETSCTCL-14203 | In all Arbitrage, Rule gets Add in started mode while add multiple rules by Pressing ENTER key continuously even in default settings "start rule on event"(Add/Update) is untick. | Bug | High |  | Done | Sheetal Vasava | Team Nikunj | urvee patel | Team Hemant
GETSCTCL-12999 | Require an Alert in Red color during rule Addition or Modification for the Loss Side in the Slice Order Algorithm for Spread Orders | New Feature | Medium |  | Done | Kashyap Chandigara | Team Nikunj | Virendra | Team Priyesh